## Slide 1: Dynamics 365 FastTrack Solution Blueprint Workshop
<Customer Name>
Workshop date: DD.MM.YYYY

## Slide 2
Success by Design
The framework is designed around 3 principles:
  Early Discovery
  Proactive Guidance
  Predictable Success
Success by Design brings the learnings and experiences from thousands of customer deployments to make your journey to the cloud smoother, faster and successful.
Success by Design is Microsoft’s prescribed framework for Dynamics 365 implementations
Faster Deployment
Higher Adoption
Maximized ROI
Notes: The Dynamics 365 engineering team brings you the learnings and experiences from 4500+ cloud deployments through Success by Design.
Success by Design (SbD) is the prescriptive guidance - approaches & recommended practices - for designing, building and deploying a Dynamics 365 solution
.
It is grounded in fundamentals of good solution architecture and design, product capabilities, and proven approaches to business process transformation and implementation.
Designed around three core principles:
Early discovery
Proactive guidance
Predictable success

## Slide 3: Initiate-Solution Blueprint Workshop
Refine your vision, identify and prioritize business scenarios, and collaborate with key stakeholders to plan for successful rollouts at your own pace.
High Level Architecture and Solution
Project Plan and Governance Model
Application Lifecycle Management and Release Plan

## Slide 4: Engagement Model
Implement
Prepare
Initiate
Operate
Get ready to start
Design
Build
Deploy
Live
Regular touchpoints
Post go-live review
& graduation
Relevant community onboarding
Deep-dive architecture discussions
Roadblock identification & mitigation
Roadmap information sharing
Preview discussions & participation
Connections with engineering
Go-Live
Success story publishing
Go-live readiness checks
Kick-off
Solution blueprint review
Customer
graduation

## Slide 5: The Role of FastTrack
In Scope
Review the answers provided
Provide findings and recommendations following the workshop presentation
Provide alternatives to product gaps identified
Highlight technical and project risks and issues (including unrealistic product expectations)
Point out gaps in the solution or project structure that can result in an unsuccessful implementation
Out of Scope
Create a solution architecture based on findings
Decide on solutions that best fit gaps identified
Code review
Provide training on product features (user or administrative)
Create comparison between ISV solutions

## Slide 6
Complete each slide providing the required information
Post-it notes should be removed: their purpose is only to provide example answers.
Skip and hide slides that are not applicable to your project.
Add slides to capture the required information if needed.
Do not hesitate to paste your own slides.
Reach out if you have questions on the format or content.
Send the completed deck at least 5 business days before the workshop.
Store the document in a shared SharePoint location if possible.
Instructions for customers and partners
How to fill this document:

## Slide 7
Complete each slide providing the required information
Each Topic section outlines the areas we want to cover along with example assets.
Put your information into the slide following the topic slide and add more slides to capture the required information if needed.
Skip and hide slides that are not applicable to your project.
Do not hesitate to paste your own slides.
Reach out if you have questions on the format or content.
Send the completed deck at least 5 business days before the workshop.
Store the document in a shared SharePoint location if possible.
Instructions for customers and partners
How to fill this document:

## Slide 8: Solution Blueprint Workshop Agenda
Agenda
Understand your Program Design, provide best practices review, highlight any risks and gaps in the plan. Product roadmap and release alignment.
Attendees: Key stakeholders from the customer and partner teams. Solution architects, functional and technical leads are mandatory.
Requirements: Solution Blueprint WS templates filled out. High level Solution Architecture completed. Project plan and team roles defined.
* Include the application topics relevant to project scope
Project governance
Implementation strategy
Change management & adoption
Process-focused solution
Business process strategy
Application architecture
Environment strategy
Application lifecycle management strategy
Data management
Integration
Performance strategy
Security strategy
Testing strategy
Application specific topics*
Program Success Strategy
Notes: Suggest the following Agenda order (Topic Order value) based on the current R2R topics.
Convention
Four digits
Common topics starts with 1
App specific topics starts with 2
  CE app starts with 20 (and 21)
  FO apps starts with 22 (these will eventually be part of Dataverse)
  Others starts with 23
1010 – Project governance
1020 – Implementation strategy
1030 – Change management & adoption
1040 – Process-focused solution
1050 – Business Process Strategy
1060 – Application Architecture
1070 – Environment strategy
1080 – Application lifecycle management (ALM) strategy
1090 – Data management
1100 – Integration
1110 – Performance strategy
1120 – Security
1130 – Testing strategy
2010 – Customer Service
2020 – Sales
2030 – Customer Insights – Data
2035 – Customer Insights - Journey
2040 – Field Service
2110 – Project Operations
2210 – Finance
2220 – Supply Chain Management
2230 – Commerce
2240 – Human Resources
2310 – Intelligent Order Management

## Slide 9
Program success strategy
Topic items
Why do we ask these questions?
Asking these questions before starting a project is crucial for several reasons:
Brief Overview of Business: Understanding the business context helps tailor the project to align with the company's mission, values, and strategy.
Business Challenges to be Addressed: Identifying challenges ensures the project focuses on solving real problems, leading to more effective and relevant solutions.
Project Goals and Objectives: Clear goals and objectives help measure progress, ensuring the project stays on track and meets its intended outcomes.
Success Measures: Defining success criteria allows for the evaluation of the project's impact, helping to determine if the project has achieved its goals.
Key Business Benefits: Understanding the benefits helps justify the project's value, ensuring it contributes positively to the business and gains stakeholder support.
Major Use Cases: Identifying use cases ensures the project addresses practical, real-world scenarios, making the solution more applicable and valuable to end-users.
By addressing these aspects upfront, you can ensure the project is well-defined, aligned with business needs, and set up for success.
Brief overview of business
Business challenges to be addressed
Project goals and objectives
Success measures
Key business benefits
Major use cases
Example assets
Use cases: Visual business mission critical use cases
Project Goals and Objectives: List goals and objectives important for business owners and decision makers.
Success measures: Help customer to define success measures for this project.

## Slide 10: Major use cases
(Add your content)

## Slide 11: Program Strategy – Success Measure Definition Help

## Slide 12
Project Governance
Topic instructions
Project governance should be designed to provide the framework and techniques to do the following:
Map business goals into actions and measures that deliver the goals
Structure, plan, and reliably, safely, and efficiently drive the project
Anticipate and avoid common issues
Detect emerging risks and divergence from the planned path and support corrective actions
Provide the right amount of flexibility and agility to respond to unexpected events and to adjust to the specific constraints of the customer’s business or project
Who will create artifacts, who will consume these? Are these available to the whole team?
The architect will be analyzing this information and sharing any recommendations accordingly.
Useful resources:
Dynamics 365 Fast Track for Dynamics - Engagement Model & Project Governance | May 13, 2021
Implement Dynamics 365 projects with effective governance - Dynamics 365 | Microsoft Learn
Topic items
Documentation Approach
Work Management
Communication
Decision Making
Roles, Responsibilities and Resourcing
Project Governance Considerations
Example assets
Project Governance Framework Diagram: Visual representation of the governance structure, roles, and responsibilities.
Project Timeline and Milestones: Visual overview of the project schedule, key milestones, and deadlines.
Status Reporting: Established templates and processes for regular progress reports and updates.

## Slide 13: Project governance
(Add your content)

## Slide 14
Implementation strategy
Topic items
Why do we ask these questions?
The questions asked as part of the "Implementation strategy" are essential to ensure the project is aligned with business goals, minimizes risks, and maximizes the chances of success. They help clarify the purpose of the implementation, identify potential challenges, and ensure that the project is well-planned and executed.
A good implementation strategy includes the following elements:
Define business objectives as goals and expected outcomes of the implementation.
Outline the project timeline, milestones, and resource allocation as part of the project planning.
Identify potential key risks and develop mitigation strategies.
Plan for managing organizational changes and user adoption as part of change management.
Ensure there is a plan for continuous communication and involvement of key stakeholders. Useful resources:
How to implement Dynamics 365 cloud solutions | Microsoft Learn
Implementation strategy methodology
Rollout model
Project schedule
Example assets
Project Governance Framework Diagram: Visual representation of the governance structure, roles, and responsibilities.
Project Timeline and Milestones: Visual overview of the project schedule, key milestones, and deadlines.
Status Reporting: Established templates and processes for regular progress reports and updates.

## Slide 15: Implementation strategy
(Add your content)

## Slide 16
Change management & adoption strategy
Topic items
Why do we ask these questions?
The questions asked as part of the "Change management & adoption strategy" are essential to ensure that the organization successfully adopts and uses the new solution. They help manage the transition, engage employees, and align the solution with business goals.
A good change management and adoption strategy includes the following elements:
Align the solution with business outcomes to ensure it meets organizational goals
Plan for executive sponsorship to provide leadership and support throughout the change
Integrate with project management teams to ensure coordinated efforts and smooth implementation
Engage employees to foster acceptance and usage of the new solution
Maintain frequent and open communication to keep all stakeholders informed and involved
Useful resources:
Define a strategy for adoption and change management | Microsoft Learn
Change management and adoption considerations
Sponsorship
Organizational alignment
Communications
Example assets
Change Management Plan: Strategy for managing change and ensuring user adoption.
Stakeholder Engagement Overview: Visual representation of key stakeholders and their roles.
Training and Communication Plan: Document outlining training schedules and communication strategies.
Adoption Metrics Dashboard: Visual tool for tracking adoption rates and user engagement

## Slide 17: Change management & adoption strategy
(Add your content)

## Slide 18
Process-focused Solution
Topic items
Why do we ask these questions?
A process-focused solution helps you define, design, build, test, and support your Dynamics 365 implementation with your end-to-end business processes as the framework. Processes are the way you deliver value to your customers and achieve your business goals. By using a process-focused approach, you can create a solution that reflects and improves your business operations, regardless of the underlying methodology.
Use your business processes to define and communicate your scope in a clear and common language.
Users understand business processes because they're expressed in the languages they know best.
Processes are richer in context than a requirements list.
Processes show the connections between different business units, roles, functions, task-level steps, and systems.
They're naturally hierarchical and can be expressed in different levels of detail, depending on their intended purpose.
Processes are the connectors that show the data and people feedback loop.
Useful resources:
Implement a solution based on your business processes - Dynamics 365 | Microsoft Learn
Process-focused considerations
Process maturity
People and organization structure
Process scope
Process implementation drivers
Template strategy
Example assets
Considerations regarding stakeholders, standardization and adoption
Roles and responsibilities, change management and communication
Process alignment with organizational and legal structure
Process drivers and requirements
Template scope and management

## Slide 19: Process-focused Solution
(Add your content)

## Slide 20
Business process strategy
Topic items
Why do we ask these questions?
The questions asked as part of the "Business process strategy" are essential to ensure that business processes are aligned with organizational goals, efficient, and adaptable to change. They help identify areas for improvement, ensure consistency, and support the overall business strategy.
A good business process strategy includes the following elements:
Define business objectives to align processes with organizational goals.
Map out current processes to identify areas for improvement
Develop process documentation to ensure consistency and clarity
Plan for process optimization to enhance efficiency and effectiveness
Establish change management to adapt processes to evolving business needs
Useful resources:
Plan an implementation strategy | Microsoft Learn
Organizational strategy
Product design to retire
Forecast to plan
Procure to pay
Plan to produce
Order to cash
Project to profit
Inventory to deliver
Acquire to dispose
Hire to retire
Record to report
Example assets
Considerations regarding stakeholders, standardization and adoption
Roles and responsibilities, change management and communication
Process alignment with organizational and legal structure
Process drivers and requirements
Template scope and management

## Slide 21: Business process strategy
(Add your content)

## Slide 22
Application architecture
Topic items
Why do we ask these questions?
The questions asked as part of the "Application architecture strategy" are essential to ensure the solution is designed to meet business requirements, is scalable, and can be maintained efficiently. They help ensure that the architecture supports the necessary functionality, performance, and security needs of the organization.
A good application architecture strategy includes the following elements:
Define the architecture design to ensure it meets business requirements and supports scalability
Outline the integration strategy to ensure seamless communication between different systems and components
Plan for security architecture to protect data and ensure compliance with regulations
Establish performance architecture to ensure the system can handle expected loads and perform efficiently.
Develop a maintenance strategy to ensure the solution can be updated and maintained with minimal disruption
Useful resources:
How to implement Dynamics 365 cloud solutions | Microsoft Learn
Example assets
Architecture Diagrams: Visual representations of the Dynamics 365 implementation including internal and external relevant components.
Dynamics components
Custom components
New third-party components
Existing third-party components
Azure components
Acquisition strategy
Application architecture considerations

## Slide 23: Application architecture
(Add your content)

## Slide 24
Environment strategy
Topic items
Why do we ask these questions?
The questions asked as part of the "Environment strategy" are essential to ensure the system is secure, compliant, and efficient. They help determine the right balance of compliance, productivity, and performance, and ensure that resources are managed effectively.
A good environment strategy includes the following elements:
Determine where users are physically located to address data compliance and residency requirements.
Identify the types of environments needed and when they are required for effective resource management.
Plan for governance and control to manage access and maintain security.
Define the environment lifecycle to ensure proper management from development to production.
Explore deployment scenarios and models to find the best fit for your organization's needs. Useful resources:
Plan your environment strategy for Dynamics 365 | Microsoft Learn
Compliance considerations
Environment strategy considerations
Tenant strategy
Environment lifecycle considerations
Pre-production environment(s)
Production environment
Geo/location considerations
Example assets
Environment Strategy Overview Diagram: Visual representation of the environment strategy, including the number and types of environments.

## Slide 25: Environment strategy
(Add your content)

## Slide 26
Application Lifecycle Management (ALM) strategy
Topic items
Why do we ask these questions?
The questions asked as part of the "Application Lifecycle Management (ALM) strategy" are essential to ensure the solution is managed effectively from conception to operation. They help ensure that the solution is developed, tested, deployed, and maintained efficiently, meeting business requirements and quality standards.
A good ALM strategy includes the following elements:
Define governance to make decisions and manage risks for your solution
Outline project management to plan, organize, and execute project activities and resources
Capture, analyze, and validate business needs through requirement management.
Design the structure and components of your solution with architecture.
Verify and validate your solution against requirements and quality standards through test management.
Useful resources:
Bring successful solutions to customers with application lifecycle management (ALM) strategies | Microsoft Learn
ALM governance
Build management
Release management
Multi-platform application strategy
Example assets
ALM Process Flow Diagram: Visual representation of the ALM stages and processes.
Requirement Management Templates: Standardized templates for capturing and validating business requirements.
Deployment and Release Management Plan: Strategy for deploying the solution to different environments

## Slide 27: ALM strategy
(Add your content)

## Slide 28
Data management
Topic items
Why do we ask these questions?
The questions asked as part of the "Data management strategy" are essential to ensure data is accessible, accurate, and secure. They help determine how data is used, stored, and managed throughout its lifecycle, ensuring it supports business operations effectively.
A good data management strategy includes the following elements:
Establish data governance to define policies and procedures for data availability, usability, quality, and security.
Develop a data architecture that outlines how data is structured, stored, and accessed.
Plan for data migration and integration to ensure smooth transfer and integration of data from various sources.
Implement data quality management practices to maintain the accuracy and relevance of data.
Ensure data security and compliance to protect data from unauthorized access and ensure regulatory compliance
Useful resources:
Manage your data in Dynamics 365 implementation projects | Microsoft Learn
Data storage
Data architecture
Data modelling
Data management considerations
Data migration
AX2012 data upgrade strategy
Example assets
Data Architecture Diagram: Visual representation of data sources, flows, and storage.
Data Governance Plan: Document outlining data management policies and practices.
Data Migration and Integration Strategy: Plan for moving and integrating data across systems.
Data Quality Management Plan: Strategy for ensuring data accuracy and reliability

## Slide 29: Data management
(Add your content)

## Slide 30
Integration strategy
Topic items
Why do we ask these questions?
Integration allows you to go beyond the boundaries of the application suite and extend processes or incorporate data assets from other sources.
Defining business goals, choosing a platform for integration, the designing the integration and choosing the right patterns are important aspects for a successful integration approach.
Identify and document the strategy
Scalability and flexibility, future-proof design
Securing required resources and skills.
Useful resources:
Integrate your Dynamics 365 apps with other solutions - Dynamics 365 | Microsoft Learn
TechTalk Integration patterns finance and operations apps - Dynamics 365 | Microsoft Learn
TechTalk Integration patterns for Dataverse - Dynamics 365 | Microsoft Learn
Integration strategy
Integration scope
Integration architecture
Example assets
Integration Architecture Diagram: Visual representation of the integration architecture, systems, and integration points.
Platform and Middleware Selection Guide: Document outlining the criteria for choosing the right platform and middleware.
Integration Pattern Overview: Visual tool for understanding different integration patterns and their use cases.
Testing and Change Management Plan: Strategy for testing integrations and managing change

## Slide 31: Integration strategy
(Add your content)

## Slide 32
Performance strategy
Topic items
Why do we ask these questions?
The questions asked as part of the "Performance strategy" are essential to ensure the system performs optimally, meets user expectations, and supports business operations effectively. They help identify potential performance bottlenecks, validate the solution's ability to handle expected loads, and ensure a smooth user experience.
A good performance strategy includes the following elements:
Define clear performance goals and metrics.
Outline types of performance tests and scenarios.
The plan for continuously monitor and optimize system performance
Plan for ensuring the system can handle increased loads and future growth
A plan for optimizing database queries, code efficiency, and resource configuration Useful resources:
Prioritize performance in your Dynamics 365 implementations | Microsoft Learn
Volumes
Example assets
Performance Testing Plan: Document outlining performance testing scenarios, goals, and results.
User Persona Profiles: Detailed profiles representing different user roles, locations, and activities.
Performance Metrics Dashboard: Visual tool for tracking performance metrics and identifying areas for improvement.
Optimization Strategy: Plan for ongoing performance monitoring and optimization

## Slide 33: Performance strategy
(Add your content)

## Slide 34
Security strategy
Topic items
Why do we ask these questions?
The questions asked as part of the "Security strategy" are essential to ensure the system is secure, compliant, and efficient. They help determine the right balance of compliance, productivity, and performance, and ensure that resources are managed effectively.
A good application security strategy includes the following elements:
Identify legal, policy, or compliance certification requirements to follow
Determine data privacy or residency requirements to meet
Plan for security validation and compliance to ensure adherence to regulations
Establish governance and control to manage access and maintain security
Consider how security affects scalability and performance to avoid future limitations
Useful resources:
Secure your Dynamics 365 project from day one | Microsoft Learn
Residency considerations
Privacy considerations
Access considerations
Compliance considerations
Example assets
Security Policies and Procedures: Document outlining security policies, procedures, and best practices.
Audit and Monitoring Reports: Reports for tracking user activities, security incidents, and compliance status.
Incident Response Plan: Strategy for managing and responding to security incidents

## Slide 35: Security strategy
(Add your content)

## Slide 36
Test strategy
Topic items
Why do we ask these questions?
When you implement a Dynamics 365 solution, you want it to meet your business needs and run smoothly. To achieve this, you need to test your solution thoroughly before you deploy it to production. Testing helps you avoid problems that could delay adoption, damage your reputation, and reduce confidence in the solution.
A good testing strategy includes the following elements:
A clear testing scope based on your business processes and requirements
A comprehensive test plan with test cycles that match your solution phases and versions
Clear objectives, source documents, and entry/exit criteria for each test type
A tracking mechanism that lets you monitor progress, results, ownership, and issues for each test case
A process for adding or modifying test cases during each test pass Useful resources:
Test your Dynamics 365 solution before deployment - Dynamics 365 | Microsoft Learn
Test Strategy TechTalk
Test approach
Test management
Test plan
Example assets
Testing Plan: Document outlining test objectives, types of tests, and test environments.
Test Cases and Scenarios: Detailed documentation of test cases and scenarios to be executed.
Test Data Management Plan: Strategy for managing and preparing test data.
Test Results and Reporting Dashboard: Visual tool for tracking test results and reporting issues.

## Slide 37: Test strategy
(Add your content)

## Slide 38: Application specific topics
Fill out topics that are relevant to your project.
This is designed to give a high level level overview of your Application use and will determine whether deep dive workshops should be scheduled for any Application related topics.

## Slide 39
Finance
Topic items
(placeholder)
Example assets
(placeholder)
(placeholder)

## Slide 40
Supply Chain Management
Topic items
(placeholder)
Example assets
(placeholder)
(placeholder)

## Slide 41
Commerce
Topic instructions
The questions asked as part of “Commerce" are important to assess your strategies and plans for delivering a integrated solution that meet the business retail objectives. They help identify areas for improvement, ensure consistency, and support the overall business strategy.
Retail landscape and architecture
Commerce capabilities and scope
Retail Channel management
Useful resources:
Microsoft Dynamics 365 Commerce documentation | Microsoft Learn
Topic items
Commerce Solution Scope
Modern Point-of-Sale
Payments
Customer and ISV Extensions
Point-of-Sale Device
Peripherals
Business Continuity
Example assets
Overview if the Retail landscape

## Slide 42
Project Operations
Topic items
(placeholder)
Example assets
(placeholder)
(placeholder)

## Slide 43
Customer Insights Journey
Topic instructions
The questions asked as part of “Customer Insights Journey" are important to assess your marketing strategy is aligned with your business processes and organizational goals, They help identify areas for improvement, ensure consistency, and support the overall business strategy.
Objectives of your Marketing efforts.
Planned use cases
Budgetary considerations.
Roles and personas involved in marketing processes.
Measuring outcomes and success on marketing activities.
Considerations re potential migration from legacy tools.
Useful resources:
Dynamics 365 Customer Insights - Journeys documentation - Dynamics 365 Customer Insights | Microsoft Learn
Topic items
Marketing strategy
Marketing scope
Example assets
Current legacy tools.
CDP (customer data platform) requirements and strategy
Documentation of planned use cases

## Slide 44: Customer Insights Journey
(Add your content)

## Slide 45
Customer Service
Topic instructions
The questions asked as part of “Customer Service" are important to assess your requirements and estimated use of features to determine the next steps and ensure your implementation makes best use of the latest features and functionality.
Omnichannel requirements
Routing requirements
Choice of carrier (1st party, 3rd party)
Requirements for IVR functionality
Multi-language requirements
Useful resources:
Dynamics 365 Customer Service implementation optimization resources - Dynamics 365 | Microsoft Learn
Topic items
Customer Service scope
Unified Routing
Voice channel
Live Chat Channel
Example assets
Planned Channels
IVR requirements
Selected Voice provider
Planned volume of incoming communication
Planned Copilot capabilities

## Slide 46: Customer Service
(Add your content)

## Slide 47
Field Service
Topic Items
Field Service scope
Work Orders
Scheduling
Mobile
Customizations
Topic instructions
The questions asked as part of “Field Service" are important to assess your requirements and estimated use of features to determine the next steps and ensure your implementation makes best use of the latest features and functionality.
Planned use of Field Service Mobile
Planned use of Connected Field Service
Planned use of Remote Assist
Licensing considerations
Identified gaps requiring customizations
Useful resources:
Dynamics 365 Field Service implementation optimization resources - Dynamics 365 | Microsoft Learn
Example assets
Planned use of Field Service Mobile, Connected Field Service and Remote Assist
Work Order generation
Identified gaps requiring customizations
Scheduling approach (manual, schedule board, automated via RSO)
Mobile and offline strategy and requirements

## Slide 48: Field Service
(Add your content)

## Slide 49
Sales
Topic Items
Sales scope
Sales Strategy
Sales Data Quality
Copilot for Sales
Monitoring, adoption and change management
Topic instructions
The questions asked as part of “Sales" are important to assess your requirements and estimated use of features to determine the next steps and ensure your implementation makes best use of the latest features and functionality.
Useful resources:
Dynamics 365 Sales documentation | Microsoft Learn
Developer Guide | Microsoft Learn
Example assets
Personas, key activities, channels
Current Sales challenges, opportunities and drivers for implementation
Current pain points that are supposed to be addressed
Sales implementation goals and expected key results
Planned use of Copilot capabilities

## Slide 50: Sales
(Add your content)